## Weekly Checklist
Task | Owner | Cadence | Mon | Tue | Wed | Thu | Fri | Flag | Notes | Last Updated
Inspect restroom supplies and restock as needed | J. Carter | Daily | ✓ | ✓ | ✓ | ✓ | ✓ | Green | All floors checked; Bay 3 low on paper towels | 2026-03-21
Review overnight cleaning crew sign-in log | M. Torres | Daily | ✓ | ✓ | ✓ |  |  | Yellow | Wed crew clocked in 22 min late — noted | 2026-03-20
Conduct exterior parking lot walk-through | D. Singh | Daily | ✓ | ✓ | ✓ | ✓ | ✓ | Green | No debris; lighting functioning | 2026-03-21
Submit weekly vendor invoice approvals to AP | K. Johnson | Weekly |  |  |  |  | ✓ | Green | 3 invoices submitted Fri; 1 pending credit memo | 2026-03-21
Verify HVAC filter replacement schedule compliance | R. Patel | Weekly |  |  |  | ✓ |  | Red | Unit 4B filter overdue by 2 weeks — escalated | 2026-03-20

## Adhoc - Projects
Initiative | Owner | Due Date | Priority | Stage | Flag | Blockers | Notes | Last Updated
Roll out new vendor credentialing portal | K. Johnson | 2026-04-15 | High | In Progress | Yellow | IT integration delayed by 2 sprints | [2026-03-10] Kickoff complete [2026-03-18] IT timeline revised to Apr 15 | 2026-03-21
Negotiate Q2 janitorial contract renewal | M. Torres | 2026-03-31 | High | Review Needed | Red | Legal redlines outstanding since Mar 12 | [2026-03-01] RFP sent to 3 vendors [2026-03-14] Legal review in progress | 2026-03-20
Install roof-deck drainage sensors, Bldg C | D. Singh | 2026-05-01 | Medium | Not Started | Green |  | [2026-03-05] Budget approved [2026-03-19] Scope finalized with contractor | 2026-03-19
Implement energy audit recommendations | R. Patel | 2026-06-30 | Medium | In Progress | Green |  | [2026-02-20] Phase 1 LED swap complete — 18% reduction [2026-03-15] Phase 2 scoped | 2026-03-15
Train facility staff on new work-order app | J. Carter | 2026-04-05 | Low | Pending | Yellow | Waiting on vendor to finalize training deck | [2026-03-12] Pilot session scheduled [2026-03-21] Deck still pending from vendor | 2026-03-21

## Quarterly Scorecard
Goal | Owner | Target | Actual | Status | Notes
Reduce work-order backlog to < 10 open items | D. Singh | < 10 open | 14 open | At Risk | Backlog spiked after 2 emergency repairs in Feb; targeting clearance by Apr 1
Achieve 98% vendor invoice on-time payment | K. Johnson | 98% | 96.2% | At Risk | 3 invoices held pending PO correction; AP process update underway
Complete all Q1 scheduled PM work orders | R. Patel | 100% complete | 91% complete | Behind | HVAC unit 4B and roof drain units deferred; rescheduled for Apr
Zero critical safety incidents across all sites | J. Carter | 0 incidents | 0 incidents | Complete | Q1 closed with clean record; near-miss log reviewed monthly

## Accountability Log
Date | Task | Owner | Original Due Date | Miss Count | Reason | Resolution | Resolved Date
2026-03-10 | Submit Q1 PM completion report | R. Patel | 2026-03-07 | 2 | Data collection delayed; vendor did not provide service logs on time | Logs obtained manually; report submitted Mar 10 with director approval | 2026-03-10
2026-03-18 | Renew janitorial contract before expiration | M. Torres | 2026-03-15 | 1 | Legal redlines not returned within agreed 5-day window | Escalated to legal director; interim extension executed
2026-03-21 | Complete HVAC filter replacement — Unit 4B | D. Singh | 2026-03-07 | 3 | Parts backordered from supplier; no substitute approved | Emergency PO issued for alternate supplier; work order rescheduled

## Dashboard
⚑ Open Flags — Red & Yellow (Standup View)
Source | Task / Initiative | Owner | Flag | Notes
Pull from Weekly | Review overnight cleaning crew sign-in log | M. Torres | Yellow | Wed crew clocked in late
Pull from Weekly | Verify HVAC filter replacement schedule compliance | R. Patel | Red | Unit 4B overdue — escalated
Pull from Adhoc | Roll out new vendor credentialing portal | K. Johnson | Yellow | IT integration delayed
Pull from Adhoc | Negotiate Q2 janitorial contract renewal | M. Torres | Red | Legal redlines outstanding
Pull from Adhoc | Train facility staff on new work-order app | J. Carter | Yellow | Waiting on vendor training deck
⚙ Bench Scorecard — Vetted Substitutes
Market | Vetted Subs | Warm Candidates | Last Updated
Northeast | 4 | 2 | 2026-03-15
Mid-Atlantic | 3 | 1 | 2026-03-10
Southeast | 5 | 3 | 2026-03-18
Midwest | 2 | 0 | 2026-03-01
📊 Week Completion Rate
Week Of | Total Tasks | Completed | Missed | Rate %
2026-03-03 | 25 | 24 | 1 | 96%
2026-03-10 | 25 | 23 | 2 | 92%
2026-03-17 | 25 | 22 | 3 | 88%
2026-03-24 | 25 | - | - | —